## Pipeline RBC October 2025
Title | Council | Department | Current Contract Expiry Date | Procurement Start Date | Contract Commencement Date | Contract Length | Extension | Planned Procurement Route (project type?)
Abbey Stadium Sports Hall Roof | Redditch | Property Services | 9/26/2025 | 2025-01-10 | 2025-12-10 | 1 | N/A | A Framework
Architects - Procurement | Redditch | Housing Strategy / Development |  | 2026-02-01 | 2026-02-03 | TBC | TBC | A Framework
Audio visual system | Redditch | Environmental Services |  |  |  | 3 TBC | Yes | A Framework
Balcony Replacement | Redditch | Housing Capital | 5/21/2026 | 2026-01-01 | 2026-01-04 | 3 | No | A Tender
Bordesley Abbey Visitor Centre Kiosk | Redditch | Property Services | 9/26/2025 | 2025-01-10 | 10/31/2025 | 1 | N/A | A Tender
Cardington Close play area enhancement | Redditch | Leisure & Arts | 2026-01-12 | 2026-01-01 | 2026-01-03 | 1 | Yes | A Framework
Carlton Close play area refurbishment | Redditch | Leisure & Arts | 6/30/2027 | 2026-01-09 | 2026-01-11 | 1 | No | A Quotation
Civil Engineering Works | Redditch | Housing Property Services |  | 2025-04-01 | 2025-06-01 | 3 | Yes | A Tender
External Cladding Improvement | Redditch | Housing Property Services |  | 2026-01-01 | 2026-01-04 | 3 | Yes | A Tender
External Staircase | Redditch | Housing Property Services |  | 2025-06-01 | 2025-07-01 | 2 |  | A Tender
Fleet replacement | Redditch | Housing Property Services |  |  |  | 2 | Yes | A Framework
Flexiroute | Redditch | Community Services |  | 2024-10-01 | 2024-01-12 | 3 | TBC | A Framework
Gutter and window cleaning | Redditch | Housing Property Services |  | 2026-01-01 | 2026-01-04 | 3 | No | A Tender
Hardware Products | Redditch | Housing Property Services |  | 2025-05-11 | 2026-06-01 | 2 | Yes | A Tender
Lowlands Lane play area refurbishment | Redditch | Leisure & Arts | 2027-01-03 | 2026-01-01 | 2026-01-03 | 1 | Yes | A Framework
Microsoft Licenses | Redditch | ICT | 2028-01-07 | 2028-01-04 | 2028-02-07 | 3 | N/A | A Framework
New Cemetary | Redditch | Environmental Services |  | 2024-01-01 |  | 2 |  | A Framework
new play areas at Matchborough and Oakenshaw | Redditch | Leisure & Arts |  | 2026-01-02 | 2026-01-05 | 1 | Yes | A Framework
Payment Processing | Redditch | Finance | 12/23/2023 |  |  | TBC | TBC | A Tender
play area installation Terrys Field Abbeydale | Redditch | Parks & Events | 11/30/2026 | 2025-01-12 | 2026-01-02 | 1 |  | A Framework
Plumbing, Heating and Gas Material Supply and Associated Service | Redditch | Environmental Services | 6/30/2026 | 2025-03-10 | 11/30/2025 | 3 + 1 | Yes | A Framework
Refurbishment of The Anchorage | Redditch | Housing Property services | 2025-01-01 | 2026-01-01 | 2025-01-04 | 1 | N/A | A Tender
Remodel - Auxerre House | Redditch | Housing Property Services |  | 2025-10-01 | 2026-01-01 | 2 | Yes | A Tender
Removals and Decants | Redditch | Housing & Community Services | 2026-01-01 | 2025-01-11 | 2026-01-01 | 3 | No | A Tender
Renewable Heating Servicing and Maintenance | Redditch | Housing Property Services |  | 2025-01-11 | 2026-01-04 | 2 | Yes | A Framework
Retrofit WAVE 3 Contractor | Redditch | Housing Property Services | 2026-10-09 | 2025-05-01 | 2025-01-10 | 4 | Yes | A Framework
Roofing Repairs and Replacement | Redditch | Housing Property Services | 10/31/2025 | 9/26/2025 | 2025-01-12 | 2 | Yes | A Tender
Springvale Rd play area upgrade | Redditch | Leisure & Arts | 6/30/2026 | 2026-01-01 | 2026-01-02 | 1 | No | A Quotation
Storage shelving | Redditch | Environmental Services |  | 9/19/2025 | 2025-01-12 | 2 | No | A Framework
Structural, QS, Project Manangement Consultancy | Redditch | Housing Capital |  | 2025-01-10 | 10/26/2025 | 3 | Yes | A Framework
Supply of PPE and clothing | Redditch | Environmental Services | 11/30/2025 | 10/17/2025 | 2025-01-12 | 2 | No | A Framework
Void Contract | Redditch | housing capital | 2028-01-03 | 2026-04-01 | 2026-01-04 | 3 | Yes | A Tender
Waterpipe Replacement & Drainage | Redditch | Housing Capital | 2025-01-09 | 10/13/2025 | 2025-03-11 | 3 | Yes | A Tender
Confidential waste collection | Joint | Property Services | 3/31/2025 | 3/30/2025 | 3/31/2025 | 1 |  | A Framework
Core Cisco Network Replacement | Joint | Business Transformation | 10/31/2030 | 2025-01-11 | 2025-01-11 | 5 | No | A Framework
eFinancials RTU extension | Joint | Finance | 9/30/2025 | 2025-01-10 | 2025-01-10 | 2 | No | A Framework
Specialist Ecology support - planning skills fund | Joint | Planning |  | 2024-01-10 | 2025-10-02 | 1 | N/A | A Framework
Temp Buildings for Election Purposes | Joint | Electoral Services | 12/31/2026 | 2022-01-01 | 2022-01-01 | 3 | TBC | A Framework